## autorisen_plan_v4
module | area | task_id | task_title | description | owner | priority | estimate | depends_on | status | started_at | updated_at | done_at | notes
Auth & Accounts | Backend | AUTH-001 | Design auth data model | Users, credentials, sessions, roles, permissions; ERD + migration scripts. | backend | P1 | 6 |  | todo |  | 2025-09-27
Auth & Accounts | Backend | AUTH-002 | Implement /auth/register + hashing | FastAPI route, Pydantic schemas, validation, bcrypt/argon2 hashing, happy-path tests. | backend | P1 | 8 | AUTH-001 | todo |  | 2025-09-27
Auth & Accounts | Backend | AUTH-003 | Implement /auth/login + JWT | Issue access/refresh tokens, rate limit, audit events. | backend | P1 | 8 | AUTH-002 | todo |  | 2025-09-27
Auth & Accounts | Backend | AUTH-004 | /auth/me and refresh flow | Protected route + token refresh endpoint + middleware. | backend | P1 | 6 | AUTH-003 | todo |  | 2025-09-27
Auth & Accounts | Backend | AUTH-005 | Security hardening & tests | Bruteforce protection, CSRF for state-changing ops, unit+integration tests. | backend | P1 | 6 | AUTH-003 | todo |  | 2025-09-27
Org & Tenants | Backend | ORG-006 | Org model + memberships | Create orgs, roles, invitations; migrations + seeds. | backend | P1 | 8 | AUTH-001 | todo |  | 2025-09-27
Org & Tenants | Backend | ORG-007 | /orgs CRUD + /orgs/{id}/members | Routes with RBAC middleware and org scoping. | backend | P1 | 8 | ORG-006,AUTH-004 | todo |  | 2025-09-27
Org & Tenants | Backend | ORG-008 | Invite & accept flow | Email invite, tokenized join, acceptance tests. | backend | P2 | 6 | ORG-007 | todo |  | 2025-09-27
Agents Gateway | Backend | AIGW-009 | Provider adapter interface | Define adapter protocol (complete, chat, embed) + error types. | backend | P1 | 6 |  | todo |  | 2025-09-27
Agents Gateway | Backend | AIGW-010 | OpenAI adapter + quotas | Implement provider with timeouts, retries, quotas, usage metering. | backend | P1 | 10 | AIGW-009,AUTH-003 | todo |  | 2025-09-27
Agents Gateway | Backend | AIGW-011 | /ai/complete¦/ai/chat routes | Normalize request/response, redact PII before egress. | backend | P1 | 8 | AIGW-010 | todo |  | 2025-09-27
Orchestrator | Backend | ORCH-012 | Run model + state machine | Design run states, retries, backoff; persistence schema. | backend | P1 | 10 | AIGW-011 | todo |  | 2025-09-27
Orchestrator | Backend | ORCH-013 | POST /flows/{name}/run | Kickoff runs; idempotency keys; cancellation. | backend | P1 | 8 | ORCH-012 | todo |  | 2025-09-27
Orchestrator | Backend | ORCH-014 | Tool registry + sandbox | Register tools, resource budgets; security guardrails. | backend | P2 | 10 | ORCH-012 | todo |  | 2025-09-27
Conversations | Backend | CONV-015 | Thread/message schema | Threads, messages, attachments; retention policy. | backend | P1 | 6 | AUTH-001 | todo |  | 2025-09-27
Conversations | Backend | CONV-016 | POST /threads, /messages | HTTP write paths with authz and org scoping. | backend | P1 | 8 | CONV-015,AUTH-004 | todo |  | 2025-09-27
Conversations | Backend | CONV-017 | WebSocket push fan-out | Real-time updates with backpressure and auth. | backend | P2 | 8 | CONV-016 | todo |  | 2025-09-27
Knowledge Base | Backend | KB-018 | Docs/chunks/embeddings schema | Models for docs, chunks, embeddings, ACL. | backend | P1 | 8 | AUTH-001 | todo |  | 2025-09-27
Knowledge Base | Backend | KB-019 | Ingestion pipeline (bg) | Async chunk + embedding jobs; failures + retries. | backend | P1 | 10 | KB-018 | todo |  | 2025-09-27
Knowledge Base | Backend | KB-020 | /kb/docs + /kb/search | Secure retrieval with ACL enforcement. | backend | P1 | 8 | KB-019 | todo |  | 2025-09-27
Scheduler & Automations | Backend | SCHED-021 | Job model + runner | At-least-once semantics; dedupe keys; jitter. | backend | P1 | 8 |  | todo |  | 2025-09-27
Scheduler & Automations | Backend | SCHED-022 | /jobs API + webhooks | Create/list jobs; signed webhook delivery. | backend | P1 | 8 | SCHED-021 | todo |  | 2025-09-27
Notifications | Backend | NOTIF-023 | Provider abstraction + templates | Render engine + provider failover. | backend | P2 | 8 |  | todo |  | 2025-09-27
Notifications | Backend | NOTIF-024 | /notify/send + events | Send endpoint; delivery logs; alerts on failures. | backend | P2 | 6 | NOTIF-023 | todo |  | 2025-09-27
Analytics & Telemetry | Backend | ANALYT-025 | Event schema + ingestion | Define event contracts; PII-safe fields; batching. | backend | P1 | 8 |  | todo |  | 2025-09-27
Analytics & Telemetry | Backend | ANALYT-026 | /events, /metrics endpoints | Ingest/write; basic rollups; dashboards seed. | backend | P2 | 10 | ANALYT-025 | todo |  | 2025-09-27
Billing & Plans | Backend | BILL-027 | Plan catalog + entitlements | Plans, limits; middleware hooks. | backend | P1 | 8 |  | todo |  | 2025-09-27
Billing & Plans | Backend | BILL-028 | Subscriptions + invoices | Gateway integration + webhooks; reconciliation. | backend | P1 | 10 | BILL-027 | todo |  | 2025-09-27
Billing & Plans | Backend | BILL-029 | Usage metering & credits | Track AI usage; per-tenant rollups. | backend | P1 | 10 | AIGW-010,BILL-027 | todo |  | 2025-09-27
Admin Console | Backend | ADMIN-030 | Health/smoke endpoints | /admin/health; per-service checks. | backend | P1 | 4 |  | done | 2025-09-27 | 2025-09-27 | 2025-09-27 | added /alive and smoke endpoints; verified
Admin Console | Backend | ADMIN-031 | Feature flags + RBAC | Flags service + guards + audit. | backend | P2 | 8 | ORG-006 | todo |  | 2025-09-27
Admin Console | Backend | ADMIN-032 | Audit views | Admin audit logs search/export. | backend | P2 | 6 | ANALYT-025 | todo |  | 2025-09-27
Environments & Delivery | DevOps | DEVOPS-033 | Docker Compose local stack | Backend, DB, Redis; seed data; make targets. | devops | P1 | 6 |  | busy | 2025-09-27 | 2025-09-27 |  | started local compose for smoke testing
Environments & Delivery | DevOps | DEVOPS-034 | Staging deploy (Heroku) | Autorisen app: build pipelines + smoke tests. | devops | P1 | 8 | DEVOPS-033 | done | 2025-09-27 | 2025-09-27 | 2025-09-27 | staging deploy validated; smoke-test passed
Environments & Delivery | DevOps | DEVOPS-035 | Prod deploy (Capecraft) | Promotion from staging; rollback plan. | devops | P1 | 6 | DEVOPS-034 | busy | 2025-09-27 | 2025-09-27 |  | starting prod promotion prep
Observability & Security | Platform | OBS-036 | Structured logs + tracing | Request IDs; OpenTelemetry exporter; dashboards. | platform | P1 | 8 |  | busy | 2025-09-27 | 2025-09-27 |  | instrumentation sprint started
Observability & Security | Platform | OBS-037 | Rate limits & WAF rules | Auth + AI routes rate limiting; basic WAF filters. | platform | P1 | 6 | AUTH-003 | busy | 2025-09-27 | 2025-09-27 |  | rate limit rules drafted
Observability & Security | Platform | OBS-038 | Runbooks & alerts | Golden signals; paging; on-call docs. | platform | P2 | 6 | OBS-036 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-001 | Design system (accessible) | Base Button/Input/Card/Typography with WCAG AA targets; focus states; keyboard nav; color-contrast checks. | frontend | P1 | 8 |  | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-002 | Onboarding checklist experience | Action-based onboarding with progress save, helpful microcopy and trust signals. | frontend | P1 | 8 | AUTH-004 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-003 | API client & auth interceptor | Typed client, attach JWT, 401 refresh; env-based baseURL. | frontend | P1 | 6 | AUTH-003 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-004 | Login page + form | Client validation, submit to /auth/login. | frontend | P1 | 5 | AUTH-003 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-005 | Register page | Submit to /auth/register, password rules. | frontend | P1 | 5 | AUTH-002 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-006 | Protected routes & RBAC | Route guards, role-based menus, org scoping. | frontend | P1 | 6 | AUTH-004,ORG-007 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-007 | Org management screens | Create org, manage members/roles, invite accept flows. | frontend | P1 | 8 | ORG-007,ORG-008 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-008 | Chat thread UI | Thread list, message composer, markdown rendering. | frontend | P1 | 8 | CONV-016 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-009 | KB upload & status | File uploader, progress, ingestion status list. | frontend | P1 | 6 | KB-019 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-010 | KB search UI | Search bar, filters, ACL-aware result rendering. | frontend | P1 | 6 | KB-020 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-011 | Run flow UI | Trigger flow run, show steps and status, cancel. | frontend | P1 | 6 | ORCH-013 | todo |  | 2025-09-27
Frontend (User & Dev Portals) | Frontend | FE-012 | Plans & subscription UI | Select plan, manage card, invoices, credits. | frontend | P1 | 8 | BILL-028,BILL-029 | todo |  | 2025-09-27
Security | Platform | SEC-001 | CSRF protection roll-out | CSRF tokens for state-changing endpoints; frontend interceptor; backend middleware. | platform | P1 | 8 | AUTH-004 | todo |  | 2025-09-27
Security | Platform | SEC-002 | Optional OAuth2 social/enterprise | OAuth2 login (Google/Microsoft) with org linking and scopes. | platform | P2 | 10 | AUTH-004 | todo |  | 2025-09-27
Security | Platform | SEC-003 | Field encryption (AES-256) | Encrypt sensitive columns (provider_keys, tokens) with KMS-managed keys. | platform | P1 | 10 | AIGW-010 | todo |  | 2025-09-27
Security | Platform | SEC-004 | Quarterly security audit | Checklist + dependency scan + penetration test summary. | platform | P2 | 6 | OBS-036 | todo |  | 2025-09-27
Validation & Data Platform | Backend | VAL-001 | Username/email availability API | /validate/username and /validate/email endpoints; org-aware constraints. | backend | P1 | 6 | AUTH-001 | todo |  | 2025-09-27
Validation & Data Platform | Frontend | VAL-002 | Debounced client validation | 300ms debounce, optimistic hints; error states wired to VAL-001. | frontend | P1 | 4 | VAL-001 | todo |  | 2025-09-27
Validation & Data Platform | Platform | VAL-003 | Redis cache for hot lookups | Cache availability checks with TTL; eviction strategy. | platform | P1 | 6 | VAL-001 | todo |  | 2025-09-27
Billing & Plans | Backend | BILL-030 | Plan tiers & quotas finalized | Free/Basic/Pro/Enterprise entitlements with usage caps. | backend | P1 | 6 | BILL-027 | todo |  | 2025-09-27
Billing & Plans | Backend | BILL-031 | Pay-per-use credits flow | Purchase, consume, and reconcile credits; receipts. | backend | P1 | 8 | BILL-028 | todo |  | 2025-09-27
Developer Ecosystem | Backend | DEV-001 | Developer revenue share engine | Monthly revenue splits with statements and export; dispute process. | backend | P1 | 10 | BILL-029 | todo |  | 2025-09-27
Developer Ecosystem | Docs | DEV-002 | Developer terms & payout policy | Clear terms (percentage, timing, clawbacks); public docs. | docs | P1 | 4 | DEV-001 | todo |  | 2025-09-27
Developer Ecosystem | Platform | DEV-003 | Agent submission pipeline | Linting, tests, security scan, staged rollout to catalog. | platform | P1 | 10 | AIGW-011 | todo |  | 2025-09-27
Developer Ecosystem | Docs | DEV-004 | Dev Portal docs & SDK | Quickstarts, API reference, example agents; TypeScript/Python SDK. | docs | P2 | 10 | DEV-003 | todo |  | 2025-09-27
Experience & Demo | Frontend | DEMO-001 | Guided tour + demo agents | Demo data toggle; highlight AI features during first run. | frontend | P1 | 6 | FE-001 | todo |  | 2025-09-27
Experience & Demo | Backend | DEMO-002 | Sample agents & seeded datasets | Seed scripts and safe sample responses showing AI in action. | backend | P1 | 6 | AIGW-011 | todo |  | 2025-09-27
Global Readiness | Frontend | GLOB-001 | Locale & timezone awareness | User profile locale/timezone; UI reflects regional formats. | frontend | P2 | 6 |  | todo |  | 2025-09-27
Global Readiness | Backend | GLOB-002 | Currency & tax formatting | Price display per locale; VAT notes for ZA; USD default. | backend | P2 | 6 | BILL-030 | todo |  | 2025-09-27
Resilience & Scale | Platform | SCALE-001 | Load & soak tests | Target p95 < 400ms simple calls; <1200ms agent runs queued. | platform | P1 | 8 | ORCH-013 | todo |  | 2025-09-27
Resilience & Scale | Platform | SCALE-002 | Uptime SLO 99.9% instrumentation | Error budget dashboards, weekly review. | platform | P1 | 6 | OBS-036 | todo |  | 2025-09-27
Resilience & Scale | Platform | SCALE-003 | Autoscaling & backpressure policies | Queue limits, circuit breakers, graceful degradation. | platform | P1 | 10 | ORCH-013 | todo |  | 2025-09-27

## normalized_plan
file | group | subgroup | task | status | _source_sheet | _snapshot_date
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | done | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | devops |  | busy | autorisen_plan_v4 | 2025-09-29
| General | devops |  | done | autorisen_plan_v4 | 2025-09-29
| General | devops |  | busy | autorisen_plan_v4 | 2025-09-29
| General | platform |  | busy | autorisen_plan_v4 | 2025-09-29
| General | platform |  | busy | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | docs |  | todo | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29
| General | docs |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | frontend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | backend |  | todo | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29
| General | platform |  | todo | autorisen_plan_v4 | 2025-09-29